LAME BRAIN ideas

# Prospectus &
Feasibility Study

A staged path from idea-development studio to a validated venture platform

“Ever have one? Come on in.”

INVESTMENT-COMMITTEE CONCLUSION

CONDITIONAL GO for a 90-day paid pop-up and concierge studio. NO-GO for a long-term flagship lease, proprietary funding platform, investor marketplace, or franchise rollout until the validation gates in this prospectus are met.

Prepared 17 July 2026 | Version 1.0 | United States planning basis

This document is a planning prospectus and feasibility study. It is not an offer to sell securities, audited financial statements, a valuation, legal advice, tax advice, or an assurance of future performance.

AT A GLANCE

# 01  Executive decision

THE RECOMMENDATION

Launch the smallest paid version that can prove willingness to pay, delivery quality, confidentiality, and repeatable economics. Preserve the storefront vision as a tested destination—not as the first irreversible cost.

Lame Brain Ideas can occupy a real gap between free mentoring, do-it-yourself AI, specialist consulting, incubators, and crowdfunding platforms. The gap is not “advice.” It is a confidential, guided transformation from an unstructured idea into decision-ready artifacts: problem definition, evidence, concept options, prototype or pitch, execution plan, and an honest next-step recommendation.

The original source concept is emotionally legible and retail-friendly: a place where ordinary people can walk in with an idea and leave with progress. The proposed three exits—take the package home, pursue rewards crowdfunding, or enter an investor pathway—are compelling when they are separated by clear gates. They become legally and operationally hazardous if they are bundled as one promise.

| Decision lens | Finding | Implication |
| --- | --- | --- |
| Customer need | Plausible, not yet measured | Test paid demand before a lease |
| Service feasibility | High for a concierge studio | Codify scope, QA, and handoffs |
| Flagship economics | Weak in base case | Do not fund on walk-in optimism |
| Platform feasibility | Conditional and regulated | Partner first; build later |
| Scalability | Unproven | Replicate only after store-level proof |

## Financial reality

| Scenario | Year 5 revenue | Year 5 EBITDA | Margin | Funding need | Break-even |
| --- | --- | --- | --- | --- | --- |
| Downside | $1.345M | ($611K) | (45.4%) | $5.128M | Beyond Y5 |
| Base | $2.010M | $75K | 3.7% | $2.648M | Year 5 |
| Upside | $2.497M | $402K | 16.1% | $2.116M | Year 4 |

Source: management-assumption financial model accompanying this prospectus. Figures are unlevered and rounded.

WHAT IS BEING EVALUATED

# 02  Source concept and strategic reframing

## What the source actually contains

The public ChatGPT share titled “Lame Brain Ideas Plan” contains one user concept prompt and one assistant response. No Canvas documents, attachments, financial files, operating manuals, or brand assets were recoverable. This prospectus therefore treats the user’s prompt as source intent and the assistant response as a set of hypotheses—not as approved strategy or evidence.

The source proposes a hip, approachable storefront—part Apple Store, Brookstone, Kickstarter, and Shark Tank—with employees called Brain Stormers, private idea intake, AI-enabled development, and three possible exits. The prior response added tiered packages, studio zones, proprietary AI engines, memberships, city targets, crowdfunding fees, investor memberships, and franchising. Those additions are useful design prompts but require validation.

## The investable reframing

CATEGORY

A guided idea-development studio with retail hospitality—not a retail store that happens to sell consulting.

Customer promise: turn ambiguity into evidence, artifacts, and a decision.

Operating unit: scoped professional-service engagements delivered through a repeatable studio workflow.

Experience advantage: easy walk-in language, tangible outputs, private rooms, workshops, and visible progress.

Platform option: rewards crowdfunding and investor introductions only after service quality, demand, and compliance are proven.

## Three exits, three distinct products

| Exit | Customer outcome | Business role | Gate |
| --- | --- | --- | --- |
| Take-home package | Research, concept, plan, prototype/pitch | Core revenue | Available from day one |
| Rewards launch | Campaign-ready assets and launch plan | Service + partner referral | Product and fulfillment readiness |
| Investor pathway | Finance-ready materials and curated introductions | Later-phase membership/network | Specialist legal design and qualified companies |

EVIDENCE BEFORE TAM

# 03  Market context

There is a large, renewing universe of people and firms forming, testing, and improving businesses. That is evidence of activity, not proof that Lame Brain Ideas can capture a fixed percentage. This study avoids a fictional top-down market-size claim and instead uses a bottom-up paid pilot to measure addressable demand by segment, channel, package, and location.

| Signal | Current evidence | Meaning for Lame Brain Ideas |
| --- | --- | --- |
| Small-business universe | 36,207,130 U.S. small businesses; 82.3% are nonemployers [S1] | Large fragmented audience; many have limited staff capacity |
| Formation intent | 531,423 seasonally adjusted business applications in June 2026 [S2] | A recurring upper funnel, not equivalent to paying customers |
| Near-term formation | 29,741 projected payroll startups within four quarters from the June cohort [S2] | Qualification matters; only a fraction progress |
| AI adoption | 7.6% of small businesses used AI during Sep 2024–Aug 2025; 8.2% among firms with fewer than five employees [S1] | AI interest is real, but adoption remains uneven |
| Business mortality | 49.2% of establishments born in 2018 survived five years [S1] | Customers need honest kill/pivot decisions, not encouragement theater |

## Why customers might pay

They lack a sequence: AI can generate options, but not an accountable process or a credible stop decision.

They need tangible outputs: evidence logs, positioning, prototypes, scope, economics, launch plan, and pitch materials.

They value confidence and speed: a facilitated sprint can replace weeks of fragmented searching and tool hopping.

They need discretion: sensitive ideas require explicit data handling, consent, access, retention, and deletion controls.

## Bottom-up demand test

The pilot should run a geo-coded funnel by audience and acquisition channel. The real serviceable market is the set of qualified prospects within the pilot catchment who convert at a sustainable acquisition cost, complete a scoped engagement, and produce sufficient revenue per delivery hour. Every marketing claim and capital decision should be downstream of that evidence.

WHO BUYS FIRST

# 04  Customer segmentation and beachhead

| Segment | Job to be done | Best entry offer | Priority |
| --- | --- | --- | --- |
| Aspiring founder | Decide whether an idea is worth pursuing | $99 diagnostic → $649 sprint | Primary |
| Existing microbusiness | Validate a new offer, channel, or operational improvement | $649 sprint → $3,750 build | Primary |
| Professional innovator | Turn domain insight into a credible side venture | $649 sprint | Secondary |
| Student/team | Structure a capstone, competition, or venture | Workshop / sponsored cohort | Secondary |
| Investor-ready company | Prepare data room, model, story, and introductions | $12,500 launch studio | Later, gated |

## Recommended beachhead

FIRST WEDGE

Local aspiring founders and existing microbusiness owners with a specific decision to make within 30 days. They are reachable through libraries, SBDCs, chambers, universities, coworking spaces, maker communities, and professional associations.

The beachhead excludes highly regulated products, complex patent strategy, medical claims, defense applications, and customers expecting guaranteed funding. These cases can be referred to specialists until the studio has a mature expert network.

## Buyer objections to test

“Why not use ChatGPT myself?”—answer with facilitation, evidence, synthesis, accountability, and artifact quality.

“Why not use SCORE or an SBDC?”—answer with paid speed, production, prototyping, and a defined deliverable; do not disparage free partners.

“Will you steal or train on my idea?”—answer with a plain-language confidentiality and AI-data policy.

“Can you get me funded?”—answer with qualification criteria and no guarantee.

THE SUBSTITUTE IS THE REAL COMPETITOR

# 05  Competitive landscape

| Alternative | Strength | Gap Lame Brain can address |
| --- | --- | --- |
| SCORE / SBDC | Free mentoring and technical assistance [S3][S4] | Production speed, tangible artifacts, retail access, guided AI |
| Solo AI tools | Cheap, immediate ideation and drafting | Scope control, evidence, accountability, privacy choices, expert review |
| Freelancers / consultants | Deep specialty and custom delivery | Integrated front door, packaged process, accessible language |
| Incubators / accelerators | Network, cohort, credibility, capital access | Walk-in accessibility; help before an application-ready venture exists |
| Maker spaces / studios | Equipment and hands-on prototyping | Business validation, story, launch plan, coordinated specialists |
| Kickstarter / Indiegogo | Audience and campaign infrastructure | Pre-campaign validation and production; platform fees are 5% plus processing [S5][S6] |
| Coworking / workshops | Community and events | Accountable end-to-end deliverable |

## Defensible advantage

The moat is not an AI prompt library. It is the compounding operating system around intake, scope, research provenance, human judgment, specialist routing, reusable templates, privacy controls, outcome measurement, and a trusted local network. The studio should be able to show how it reached a recommendation and where uncertainty remains.

POSITIONING

A place where your idea gets worked—not merely admired, generated, or pitched.

## Brand risk

“Lame Brain” is memorable and self-deprecating, but it may be heard as insulting or ableist. Treat the mark, domain, trademark availability, and customer interpretation as unvalidated. Run blind name tests before investing in signage or filing strategy; retain the category promise even if the name changes.

SELL A DECISION, NOT HOURS

# 06  Offer architecture and pricing

| Offer | Working price | Delivery hours | Core output | Conversion role |
| --- | --- | --- | --- | --- |
| Quick Diagnostic | $99 | 1 | Decision brief, unknowns, next step | Paid qualification |
| Idea Sprint | $649 | 4 | Problem evidence, concept options, scorecard, plan | Core entry product |
| Venture Build | $3,750 | 20 | Research, proposition, prototype/pitch, economics | Main project product |
| Launch Studio | $12,500 | 60 | Campaign/fundraising readiness package | Selective premium product |
| Founder Membership | $99/mo | Gated | Office hours, accountability, events, lab access | Recurring relationship |

All prices are working assumptions, not market evidence. The accompanying workbook calculates service revenue from capacity, utilization, delivery hours, and package mix.

## Scope controls

Every engagement starts with a signed statement of work, decision question, deliverable list, exclusions, customer responsibilities, and revision limit.

Specialist work—legal, patent, engineering certification, clinical, tax, regulated claims—requires a qualified provider and separate scope.

The studio owns its methods and templates; the customer owns paid-for custom deliverables subject to licensed inputs and third-party rights.

A kill or pause recommendation is a successful outcome when evidence does not support further spend.

## Pricing experiments

Test three price cells for the Idea Sprint ($499, $649, $799) and two formats (in-person and hybrid). Measure conversion, completion time, realized revenue per delivery hour, customer-reported value, referral, rework, and downstream package conversion. Do not discount Launch Studio until the team can estimate delivery variance.

RETAIL HOSPITALITY, PROFESSIONAL DISCIPLINE

# 07  Customer journey and studio experience

- Welcome and fit check: a host translates the idea into a decision question and screens prohibited or specialist-only work.

- Confidential intake: the customer chooses data-sharing and AI-processing permissions before any sensitive content is entered.

- Paid diagnostic: a Brain Stormer identifies evidence gaps, risks, and the best next package.

- Build sprint: facilitated research, synthesis, concept development, and prototype/pitch creation, with visible milestones.

- Red-team review: a second reviewer checks evidence, claims, feasibility, scope, and customer-ready quality.

- Exit decision: take the package, enter a rewards-launch pathway, enter a legally designed investor-readiness pathway, pause, or stop.

## Physical format

| Pilot pop-up | Modeled flagship |
| --- | --- |
| 800–1,200 sq. ft. or partner-hosted | 3,200 sq. ft. visible service location |
| One welcome/meeting area plus two private rooms | Welcome bar, private build rooms, flex workshop, prototype bench |
| Light buildout; movable furniture; short commitment | Modeled at $560K leasehold improvements plus $260K equipment/technology |
| Goal: prove demand and workflow | Goal: deliver at scale after economics are proven |

A suburban mixed-use, university-adjacent, or neighborhood center may offer better parking, recurring local traffic, and lower occupancy risk than a prestige downtown flagship. CBRE reported average U.S. retail asking rent of $24.59 per square foot and 4.9% availability in Q1 2026; the model uses $30 base rent plus $9 NNN/CAM to reflect a visible service location [S7]. Local broker proposals must replace this national benchmark.

A SERVICES ENGINE IN A STOREFRONT SHELL

# 08  Operating model and staffing

The base model assumes five delivery FTEs: one store GM/senior practitioner and four Brain Stormers. It also includes community/operations support and one-half prototype specialist FTE. This staffing is intentionally senior because customers are paying for judgment and synthesis, not access to software.

| Role | Base assumption | Accountability |
| --- | --- | --- |
| Store GM / Senior Brain Surgeon | $120K salary | P&L, QA, difficult engagements, team utilization |
| Brain Stormer ×4 | $78K each | Intake, research, synthesis, facilitation, delivery |
| Community / operations | $75K | Events, scheduling, partners, customer operations |
| Prototype specialist, 0.5 FTE | $90K full-time equivalent | Mockups, lab workflow, specialist routing |
| Benefits and payroll burden | 20% | Modeled on salaries |

BLS reported May 2024 median pay of $101,190 for management analysts and $76,950 for market research analysts. These are national occupational anchors, not local offers or proof of recruiting supply [S8][S9].

## Standard delivery workflow

Intake → scope → consent → evidence plan → build → red-team → customer review → exit recommendation → outcome follow-up.

Every deliverable carries a version, owner, source log, assumptions, unresolved questions, and human approver.

Utilization is measured on paid client delivery hours; coaching, training, sales, R&D, and quality review are planned separately.

No employee is paid based on investment dollars raised or securities transactions without specialized legal approval.

HOW THE WORK SHOULD BE GOVERNED

# 09  Agentic roles and project skills

| Assigned role | Core skills | Decision/output |
| --- | --- | --- |
| Managing Partner / IC Lead | strategy, synthesis, stage gates | Go/no-go and capital sequence |
| Venture Architect | business model, offer design, experimentation | Service ladder and validation plan |
| Market Research Lead | primary-source research, segmentation, competitor mapping | Evidence register and beachhead |
| Retail Experience & Operations Lead | service design, staffing, site operations | Journey, footprint, SOPs |
| Financial Modeling & Feasibility Lead | unit economics, scenarios, cash planning | Five-year model and checks |
| Product & AI Systems Architect | workflow, data governance, tooling, provenance | Secure human-in-the-loop platform |
| Risk/IP/Regulatory Workstream Lead | issue spotting, control design, specialist routing | Risk register and counsel briefs |
| Brand & CX Strategist | naming, positioning, retail communication | Name test and messaging |
| Evidence & Deliverable Steward | versioning, QA, source hygiene | Decision-ready artifact set |

REQUIRED EXTERNAL SPECIALISTS

Startup/securities counsel, IP counsel, privacy/security counsel, CPA/tax adviser, commercial real-estate broker, architect/contractor, insurance broker, and—in later phases—an SEC-registered intermediary. Agentic work prepares evidence and briefs; it does not replace licensed advice.

## Decision rules

Source intent is preserved; assistant-generated additions remain hypotheses until approved or validated.

Primary sources outrank market-size marketing pages and unattributed benchmarks.

Financial inputs are editable assumptions; formulas, checks, and source notes are visible.

No downstream funding or expansion stage may hide upstream service-economics failure.

TRUST IS PART OF THE PRODUCT

# 10  AI, data, and intellectual-property architecture

The safest initial architecture is a controlled service workspace, not a customer-facing autonomous “idea engine.” Human practitioners select tools, document sources and assumptions, and approve customer deliverables. The NIST AI Risk Management Framework provides a voluntary structure for managing AI risks and should inform governance [S10].

| Control domain | Minimum launch control |
| --- | --- |
| Consent | Separate confidentiality agreement, service terms, and explicit AI-processing choices |
| Data classification | Public, internal, confidential, highly restricted; prohibited data categories defined |
| Model access | Approved enterprise/API tools; training on customer data disabled where contractually available |
| Access | Least privilege, MFA, role-based workspaces, encrypted storage and transfer |
| Retention | Customer-visible retention period, deletion workflow, backup handling, legal holds |
| Provenance | Source log, prompt/output trace where appropriate, licensed asset record, human sign-off |
| Quality | Evidence check, hallucination check, claims review, second-person red-team on premium work |
| Incident response | Owner, escalation tree, customer notice criteria, preserved logs, postmortem |

## IP posture

Do not promise that an AI-assisted output is automatically protectable. The U.S. Copyright Office has emphasized human authorship, and the USPTO’s revised inventorship guidance states that only natural persons may be named inventors while AI may function as a tool [S11][S12]. Record meaningful human contributions, third-party inputs, licenses, and invention chronology. Route patentability, freedom-to-operate, trademark, and ownership questions to counsel.

SEPARATE SERVICE, LAUNCH, AND SECURITIES LANES

# 11  Regulatory and legal feasibility

| Area | Risk | Phase-appropriate response |
| --- | --- | --- |
| Confidentiality | Ideas may include trade secrets or personal data | Plain-language NDA, intake choices, secure workflow, no blanket secrecy claims |
| IP ownership | Mixed human/AI/third-party contributions | Engagement terms, provenance, assignment/license language, counsel review |
| Rewards crowdfunding | Fulfillment, consumer claims, platform rules | Prepare campaigns; use established platforms; verify claims and budgets |
| Securities crowdfunding | Offering, intermediary, communications, compensation | Use one SEC-registered broker-dealer or funding portal; specialist counsel [S13] |
| Investor community | Broker/dealer, adviser, solicitation, conflicts | No transaction-based compensation; design referral and membership model with counsel |
| Franchising | Franchise Rule disclosure and state laws | Defer; obtain franchise counsel and FDD strategy before offering franchises [S14] |
| Customer claims | “Validated,” “investable,” or “fundable” can mislead | Define criteria, disclose uncertainty, prohibit guarantees |

Regulation Crowdfunding permits eligible companies to raise up to $5 million in a 12-month period, but transactions must occur through a single SEC-registered intermediary [S13]. SEC statistics through 31 December 2025 show 9,461 filed offerings, 4,303 offerings reporting proceeds, and $1.546 billion in reported proceeds—evidence that the channel exists, not proof that a new studio should operate the channel [S15].

BOUNDARY

In the first phase, Lame Brain Ideas sells development services. It does not hold customer funds, promise capital, operate a securities marketplace, recommend securities, or receive transaction-based compensation.

BUILD TRUSTED DISTRIBUTION BEFORE PAID MEDIA SCALE

# 12  Go-to-market and partnerships

## Channel sequence

- Founder-led discovery: 40–60 interviews and 12 paid concierge engagements across the two primary segments.

- Partner-hosted clinics: libraries, SBDCs, SCORE chapters, universities, chambers, coworking spaces, maker communities, and professional groups.

- Pop-up acquisition: short-run storefront or embedded studio with geo-coded booking, transparent packages, and weekly workshops.

- Referral engine: alumni introductions, expert partners, accountants, attorneys, designers, engineers, and local lenders—subject to conflict and compensation rules.

- Selective paid acquisition: only after segment-level conversion, contribution, and payback are measured.

## Partner posture

SCORE offers no-cost, confidential mentoring, and SBDCs provide individualized advising and technical assistance [S3][S4]. These organizations are natural complements and referral partners. Lame Brain Ideas should sell structured production and speed around—rather than compete with—their public-service value.

| Metric | Pilot target | Why it matters |
| --- | --- | --- |
| Qualified lead → paid diagnostic | ≥20% | Demand and message fit |
| Diagnostic → Idea Sprint+ | ≥35% | Value ladder conversion |
| Blended service revenue / delivery hour | ≥$200 | Labor and occupancy capacity |
| Customer acquisition payback | ≤90 days | Capital-efficient growth |
| Referral / repeat share | ≥30% by month 6 | Trust and durable demand |
| NPS | ≥50 | Experience and referral potential |
| Critical privacy/confidentiality incidents | 0 | License to operate |

CAPACITY BEFORE OPTIMISM

# 13  Financial model design

The financial model is a single-store, unlevered planning model with five full operating years. It uses service capacity, utilization, delivery hours, prices, package mix, memberships, later-stage gated revenue, staffing, occupancy, operating expenses, startup uses, working capital, and maintenance capital. It is not a valuation and does not assume debt service or net operating loss tax benefits.

| Driver | Base assumption | Interpretation |
| --- | --- | --- |
| Delivery capacity | 5 FTE × 1,450 client hours = 7,250 hours | Annual practical capacity before utilization |
| Paid utilization | 38%, 52%, 65%, 75%, 82% | Aggressive maturation; must be measured |
| Service mix | 15% / 35% / 32% / 18% by hours | Quick / Sprint / Build / Launch |
| Weighted service rate | $169 per paid client hour | Based on working prices and package mix |
| Membership | $99 per month | 110 average members in Y1 to 420 in Y5 |
| Occupancy | 3,200 sq. ft.; $30 rent + $9 NNN/CAM | Visible service location; local quotes required |
| Opening uses | $995K | $560K buildout plus FF&E, tech, pre-open, deposits |
| Minimum cash buffer | $250K | Financing need preserves this balance |

Service gross margin appears high because most delivery payroll is treated as fixed operating expense. The management focus should therefore be paid utilization, realized revenue per paid hour, project variance, and gross profit after specialist pass-through—not gross margin alone.

MODEL USE

Edit blue assumption cells, review green cross-sheet formulas, and keep the Checks sheet at PASS. Replace management assumptions with signed quotes, actual invoices, and measured funnel data as they become available.

BASE CASE

# 14  Five-year single-store projection

| USD | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 |
| --- | --- | --- | --- | --- | --- |
| Revenue | $673,932 | $967,500 | $1,289,705 | $1,672,180 | $2,009,924 |
| Gross profit | $582,823 | $836,244 | $1,106,852 | $1,413,694 | $1,682,519 |
| Operating expenses | $1,197,200 | $1,209,066 | $1,357,248 | $1,476,814 | $1,607,837 |
| EBITDA | ($614,377) | ($372,822) | ($250,396) | ($63,120) | $74,681 |
| EBITDA margin | (91.2%) | (38.5%) | (19.4%) | (3.8%) | 3.7% |
| Net income | ($778,377) | ($538,844) | ($419,320) | ($235,914) | ($103,129) |

Base case reaches positive EBITDA in Year 5, but net income remains negative after depreciation. Revenue includes gated rewards-platform fees beginning Year 3 and investor memberships beginning Year 4.

## Interpretation

The flagship is not attractive as a conventional store rollout on the base assumptions. It consumes capital for four operating years and reaches only a 3.7% Year 5 EBITDA margin. The model can become compelling only if the pilot proves higher realized pricing, materially better utilization, leaner fixed staffing, or a scalable recurring product without sacrificing trust and quality.

CAPITAL MUST FOLLOW EVIDENCE

# 15  Funding need and scenario sensitivity

| Base funding use | Amount | % of $2.648M |
| --- | --- | --- |
| Opening uses | $995,000 | 37.6% |
| Operating ramp / working capital | $1,403,209 | 53.0% |
| Minimum cash buffer | $250,000 | 9.4% |
| Total modeled external funding | $2,648,209 | 100.0% |

Scenario factors recalculate utilization, price, membership/events, operating cost, and opening capital. Funding figures include the modeled minimum cash buffer.

The downside case is existential: $5.13 million of funding and no five-year break-even. The upside case is investable only relative to the base: $2.12 million of funding and a 16.1% Year 5 EBITDA margin, with positive EBITDA in Year 4. Because the range is driven by variables a paid pilot can measure, committing flagship capital before validation would buy uncertainty rather than remove it.

RECOMMENDED CAPITAL SEQUENCE

Stage A: authorize a capped $150K–$250K validation budget for 90–180 days. Stage B: consider approximately $2.65M of flagship funding only after demand, delivery, privacy, pricing, and utilization gates are independently evidenced. Structure and sources of capital require tax and legal advice.

TEN STORES ARE NOT THE PLAN

# 16  Expansion stress test

The workbook includes an intentionally aggressive illustrative path to ten stores by Year 7: one initial store, another in Year 4, two in Year 5, three in Year 6, and three in Year 7. Each new store is assumed to follow the same slow maturation curve while central platform costs increase.

| Metric | Year 4 | Year 5 | Year 6 | Year 7 |
| --- | --- | --- | --- | --- |
| Total stores | 2 | 4 | 7 | 10 |
| Total store revenue | $2.346M | $4.325M | $7.317M | $11.308M |
| Consolidated EBITDA | ($1.127M) | ($2.377M) | ($4.262M) | ($5.646M) |
| Consolidated EBITDA margin | (48.1%) | (55.0%) | (58.3%) | (49.9%) |
| Cumulative growth capex | $1.995M | $3.995M | $6.995M | $9.995M |

CONCLUSION

Do not franchise, roll out, or build central-platform overhead on the modeled maturation curve. Expansion should wait until one unit sustains attractive four-wall economics and the second unit reproduces them without founder heroics.

## Expansion gates

Trailing six-month four-wall EBITDA margin ≥15% after a normalized manager salary.

Paid delivery utilization ≥70% without overtime or quality deterioration.

At least 30% of business from repeat, referral, membership, or contracted partner channels.

Second location opens within ±10% of approved capex and reaches breakeven within 24 months.

Documented training, QA, privacy, and incident controls pass an external review.

WHAT CAN FAIL

# 17  Feasibility scorecard and principal risks

| Dimension | Current score | Rationale | Next proof |
| --- | --- | --- | --- |
| Problem / demand | 3 / 5 | Need is plausible; willingness to pay unknown | Paid conversion by segment |
| Service delivery | 4 / 5 | Concierge workflow is feasible | Scope variance, QA, throughput |
| Flagship economics | 2 / 5 | Base margin weak and capital intensive | Pilot unit economics and local quotes |
| Technology | 4 / 5 | Can start with controlled existing tools | Security/privacy assessment |
| IP / legal | 3 / 5 | Manageable for services; higher risk in funding lane | Counsel-approved terms and boundaries |
| Scale / franchise | 1 / 5 | No replicated unit or playbook | Two profitable units and audited SOPs |
| Overall | CONDITIONAL | Studio first; platform and rollout gated | 90-day validation scorecard |

## Principal risk register

| Risk | Impact | Leading indicator | Mitigation |
| --- | --- | --- | --- |
| Customers choose free/DIY alternatives | High | Low diagnostic conversion | Sharper deliverables, segment focus, partner channels |
| Projects overrun | High | Hours/package exceed plan | Scope gates, revision caps, red-team templates |
| Underutilized fixed team | High | Paid utilization below 50% | Variable staffing, cohorts, partner-hosted format |
| Confidentiality or AI incident | Critical | Control exception / complaint | Consent, access, encryption, deletion, response plan |
| Funding claims create regulatory exposure | Critical | Staff implies guarantees or transaction role | Training, scripts, counsel, registered intermediaries |
| Brand alienates target customers | Medium | Negative unaided name reaction | Blind testing, alternate names, trademark review |
| Buildout and lease overrun | High | Bids exceed allowance | Short pilot, landlord concessions, fixed bids, contingencies |

THE NEXT CAPITAL SHOULD BUY ANSWERS

# 18  Ninety-day validation program

| Period | Work | Evidence produced |
| --- | --- | --- |
| Days 1–15 | Counsel issue list; customer interviews; name test; package prototypes; partner outreach | Risk boundaries, scripts, first demand map |
| Days 16–45 | Twelve paid concierge engagements; time tracking; three price cells; artifact QA | Realized rate, scope variance, customer value |
| Days 46–75 | Partner-hosted clinics/pop-up; cohort workshop; referral tests; security tabletop | Channel conversion, throughput, incident readiness |
| Days 76–90 | Repeat sales; second-review audit; updated model; IC decision | Measured economics and go/pivot/stop recommendation |

## Hard gates for a lease search

At least 100 paid engagements or an equivalent contracted revenue base across the validation period.

Three-month trailing revenue run-rate of at least $100K per month or a credible contracted bridge to it.

Blended service revenue per paid delivery hour ≥$200 and package contribution margin ≥65% after specialist pass-through.

Paid utilization ≥60% in a lean delivery team, with premium-deliverable rework below 15%.

Lead-to-paid conversion ≥20%, acquisition payback ≤90 days, and repeat/referral share ≥30%.

NPS ≥50, no critical privacy/confidentiality incidents, and counsel-approved customer terms.

Two local site scenarios with signed landlord economics, contractor ranges, and downside covenant headroom.

DECISION RULE

Missing one hard gate does not automatically kill the venture; it forces a documented remedy, a lower-capital format, or a stop decision before a long-term obligation.

OPTIONALITY BY DESIGN

# 19  Twenty-four-month roadmap

| Stage | Months | Objective | Exit criterion |
| --- | --- | --- | --- |
| Discovery | 0–2 | Prove target problem and paid diagnostic | 12 paid cases; no critical control gap |
| Concierge studio | 2–6 | Prove offer mix, delivery, and referrals | Economics and quality thresholds met |
| Pop-up / embedded studio | 6–12 | Prove location-assisted acquisition and events | Sustained run-rate and utilization |
| Flagship diligence | 9–15 | Site, bids, financing, security, team | IC approval against downside case |
| Flagship launch | 15–24 | Operate one controlled unit | Six months of stable four-wall KPIs |
| Platform options | 18+ | Rewards partnerships; investor lane design | Qualified pipeline, counsel, intermediary partners |
| Replication | After proof | Open second company-owned unit | Reproducible economics and playbook |

## What stays deferred

Proprietary crowdfunding infrastructure, customer fund custody, or transaction processing.

Investor marketplace economics or transaction-dependent fees.

Custom AI model training on customer ideas.

Franchise sales, area development, or a ten-store capital plan.

Permanent flagship signage or major buildout before name and site validation.

MAKE THE GATES OPERATIONAL

# 20  Management dashboard and decision rights

| Dashboard | Weekly | Monthly | Quarterly / gate |
| --- | --- | --- | --- |
| Demand | Leads, bookings, conversion | CAC, payback, channel mix | Segment and market decision |
| Delivery | Hours, WIP, scope exceptions | Utilization, realized rate, rework | Package/pricing reset |
| Customer | Completion, issues | NPS, referrals, outcomes | Promise and quality review |
| Financial | Revenue, cash, commitments | P&L, forecast, runway | Capital and lease gate |
| Risk | Access/control exceptions | Incidents, deletion, claims audit | Counsel/security review |
| People | Capacity, schedule | Training, quality, retention | Staffing architecture |

## Decision rights

The Managing Partner / IC Lead owns go/no-go decisions after written recommendations from the financial, market, operating, product, and risk workstreams. The Store GM owns normal customer and scheduling decisions within approved scope. Privacy, security, IP, and securities exceptions require a named specialist approver. No sales goal can override a stop, referral, or disclosure obligation.

SINGLE SOURCE OF TRUTH

The live financial workbook, evidence register, assumptions log, decision log, and current prospectus version together form the operating record. Marketing slides may summarize them but may not silently change the underlying case.

A PROSPECTUS, NOT AN OFFERING

# 21  Capital strategy and prospective fit

The venture should seek capital that matches the proof stage. The first dollars should fund experiments, secure delivery, and decision-quality data. A conventional multi-unit retail story is premature; an evidence-driven service-and-platform option is more credible.

| Capital stage | Indicative need | Appropriate use | Potential fit |
| --- | --- | --- | --- |
| Validation | $150K–$250K | Discovery, paid cases, pop-up, legal/security, prototype brand | Founder capital, aligned angels, grants/sponsors, revenue |
| Flagship | ~$2.65M base modeled need | Opening uses, operating ramp, cash buffer | Patient equity, strategic partners; structure after advice |
| Platform / replication | Not yet estimable | Technology, central team, second unit | Only after four-wall and compliance proof |

## Prospective partner profile

Values customer outcomes and controlled experimentation over vanity store count.

Can contribute founder distribution, community partnerships, professional-service operations, retail service design, or regulated-platform experience.

Accepts that a kill, pivot, or low-capital format may be the correct result of validation.

Does not require securities activity, franchise sales, or unproven revenue to support the initial thesis.

Any actual financing process requires a separate capital plan, entity and tax analysis, investor materials, risk disclosures, governance terms, and counsel-reviewed offering pathway. The financial model’s “required financing” line is a cash-need calculation, not a proposed security.

PRESERVE THE AMBITION BY SEQUENCING IT

# 22  Conclusion

Lame Brain Ideas is feasible as a paid idea-development studio. Its storefront warmth, named guides, visible workflow, and tangible exits can make professional innovation support accessible to customers who will not enter an accelerator or hire a traditional consultancy. Existing AI tools make the service faster, but they also make undifferentiated advice easier to substitute. The company must therefore earn trust through facilitation, evidence, privacy, judgment, and outputs.

It is not yet feasible as a capital-heavy flagship network or vertically integrated funding platform. The base financial model reaches only $75K of Year 5 EBITDA on $2.01M of revenue after requiring approximately $2.65M in external funding. The downside is severe, and the illustrative ten-store rollout compounds losses. Those facts are not reasons to abandon the idea; they are reasons to run the right experiment.

FINAL RECOMMENDATION

Authorize a lean, paid, secure 90-day validation program with a capped budget and hard gates. Update the model with actuals. Proceed to a pop-up, then a flagship, only when the economics and controls—not enthusiasm—justify the next obligation.

## Immediate owner actions

- Approve or revise the customer promise, beachhead segment, four working packages, and no-guarantee funding boundary.

- Commission the legal/privacy issue list and brand/trademark screening before public intake.

- Recruit 12 paid concierge customers and three partner hosts; track time, evidence, conversion, quality, and outcomes.

- Replace rent, buildout, insurance, wage, software, and specialist assumptions with local quotes.

- Reconvene the investment committee at Day 90 with the updated workbook and a go/pivot/stop memorandum.

MODEL MECHANICS

# A  Financial appendix

## Revenue logic

Paid delivery hours = delivery FTE × available client hours per FTE × paid utilization. Package engagements = paid delivery hours × package hours mix ÷ delivery hours per engagement. Service revenue = engagements × price. Membership, events, lab add-ons, rewards fees, and investor memberships are modeled separately; rewards and investor revenue remain explicitly gated.

## Cash logic

Unlevered cash flow = EBITDA – cash taxes – change in net working capital – maintenance capital – opening uses. Required financing equals the most negative cumulative cash position plus the minimum cash buffer. The model assumes financing arrives pre-open and does not model debt interest, financing fees, valuation, ownership dilution, or investor returns.

## Scenario logic

| Driver | Downside | Base | Upside |
| --- | --- | --- | --- |
| Utilization factor | 0.8× | 1.0× | 1.2× |
| Price factor | 0.9× | 1.0× | 1.1× |
| Membership/event factor | 0.7× | 1.0× | 1.3× |
| Operating cost factor | 1.1× | 1.0× | 1.1× |
| Opening capex factor | 1.2× | 1.0× | 1.0× |

All outputs should be read with the live workbook. The workbook includes separate Assumptions, Unit Economics, P&L, Cash Flow, Scenarios, Ten-Store Rollout, Checks, and Sources sheets. Formula checks confirm structural consistency, not commercial truth.

PRIMARY AND AUTHORITATIVE EVIDENCE

# B  Research source register

[S1] Frequently Asked Questions About Small Business, 2026. U.S. Small Business Administration Office of Advocacy. Small-business counts, nonemployer share, AI-use estimates, openings, and survival. Source

[S2] Business Formation Statistics, June 2026. U.S. Census Bureau. Business applications and projected employer startups; released 9 July 2026. Source

[S3] SCORE’s Small Business Services. SCORE. No-cost, confidential mentoring benchmark. Source

[S4] Small Business Development Centers. U.S. Small Business Administration. Individualized advising and technical-assistance benchmark. Source

[S5] What are the fees?. Kickstarter Support. 5% platform fee plus roughly 3%–5% payment processing on successfully funded projects. Source

[S6] Fees & Pricing for Campaigners. Indiegogo Support. 5% platform fee plus payment processing. Source

[S7] Q1 2026 U.S. Retail Figures. CBRE. Average asking rent, availability, and suburban-versus-downtown context. Source

[S8] Management Analysts. U.S. Bureau of Labor Statistics. May 2024 median pay and 2024–34 outlook. Source

[S9] Market Research Analysts. U.S. Bureau of Labor Statistics. May 2024 median pay and 2024–34 outlook. Source

[S10] AI Risk Management Framework. National Institute of Standards and Technology. Voluntary AI-risk governance framework. Source

[S11] Copyright and Artificial Intelligence, Part 2: Copyrightability. U.S. Copyright Office. Human-authorship analysis for generative-AI outputs. Source

[S12] Revised Inventorship Guidance for AI-Assisted Inventions. U.S. Patent and Trademark Office. Natural-person inventorship and AI as a tool. Source

[S13] Regulation Crowdfunding. U.S. Securities and Exchange Commission. Offering limit and registered-intermediary requirements. Source

[S14] Franchise Rule. U.S. Federal Trade Commission. Federal franchise disclosure framework. Source

[S15] Regulation Crowdfunding Offerings. U.S. Securities and Exchange Commission. Offering and reported-proceeds statistics through 31 December 2025. Source

## Source-concept record

Public ChatGPT share: Lame Brain Ideas Plan. Accessed 17 July 2026. The share contained one user prompt and one assistant response; no Canvas or file attachments were recoverable.

READ BEFORE RELIANCE

# C  Important qualifications

The financial model is based on management assumptions. No historical operating data exists in the source package.

National data does not establish local demand, rent, wage, buildout, insurance, or customer-acquisition economics.

The word “validated” means evidence was collected against stated criteria; it does not guarantee commercial, technical, legal, or funding success.

Crowdfunding proceeds and platform activity are contextual evidence, not revenue forecasts for Lame Brain Ideas.

Customer confidentiality cannot be guaranteed absolutely. Controls reduce risk and must be described honestly.

AI-assisted work can contain errors, omissions, bias, unlicensed material, or unsupported claims; human review and specialist referral remain essential.

Any securities, franchise, IP, privacy, employment, lease, tax, or consumer-protection decision requires jurisdiction-specific professional advice.

The recommended next action is validation, not fundraising promotion. This prospectus should be updated when pilot evidence, bids, counsel advice, and actual customer outcomes replace assumptions.